## Sheet1
FUNDED AND INDICATIVE MEDIUM TERM PLAN FOR FLOOD RISK MANAGEMENT WALES CAPITAL PROGRAMME (2018/2019 ONWARDS)
APPROVED June 2018
PROJECT | LOCAL AUTHORITY | PROJECT TYPE | CONFIRMED FUNDING (£) | INDICATIVE FUNDING (£) | [8 empty] | TOTAL CONFIRMED AND INDICATIVE FUNDING (£) | PROJECT STAGE / ACTIVITY | [9 empty] | NUMBER OF HOUSEHOLDS WITH REDUCED FLOOD RISK | NUMBER OF BUSINESSES WITH REDUCED FLOOD RISK | NUMBER OF PROPERTIES ISSUED WITH INDIVIDUAL PROTECTION MEASURES | UK BIODIVERSITY ACTIONPLAN Biodiversity and Habitat EnhancmentITAT CREATED (TERRESTRIAL) (Ha) | UK BIODIVERSITY ACTIONPLAN Biodiversity and Habitat EnhancmentITAT CREATED (INTER-TIDAL) (Ha)
|  |  | 2018 - 2019 YR 1 (£) | 2019 - 2020 YR 2 (£) | 2020 - 2021 YR 3 (£) | 2021 - 2022 YR 4 (£) | 2022 - 2023 YR 5 (£) | 2023 - 2024 YR 6 (£) | 2024 - 2025 YR 7 (£) | 2025 - 2026 YR 8 (£) | 2026 - 2027 YR 9 (£) | 2027 ONWARDS YR 10+ (£) | 2018-19 TO 2027+ | 2018 - 2019 YR 1 (£) | 2019 - 2020 YR 2 (£) | 2020 - 2021 YR 3 (£) | 2021 - 2022 YR 4 (£) | 2022 - 2023 YR 5 (£) | 2023 - 2024 YR 6 (£) | 2024 - 2025 YR 7 (£) | 2025 - 2026 YR 8 (£) | 2026 - 2027 YR 9 (£) | 2027 ONWARDS YR 10+ (£) | 2018-19 TO 2027+ TOTAL | 2018-19 TO 2027+ TOTAL | 2018-19 TO 2027+ TOTAL | 2018-19 TO 2027+ TOTAL | 2018-19 TO 2027+ TOTAL
Abertillery IA | Blaenau Gwent - Blaenau Gwent | Defence |  |  | <50k | <100k | <1,000k | [5 empty] | <2,500k |  |  | Appraisal | Design | Construction
Abertillery & Six Bells - Structural Assessment | Blaenau Gwent - Blaenau Gwent | Maintenance |  |  | <50k | <50k | [6 empty] | <100k |  |  | Appraisal | Maintenance
Aberbeeg Flow Monitoring Station | Blaenau Gwent - Blaenau Gwent | Water Resources | <5k | [9 empty] | <5K | Completion
Cwm IA | Blaenau Gwent - Blaenau Gwent | Defence | [5 empty] | <50k | <100k | <1,000k |  |  | <2,500k | [5 empty] | Appraisal | Design | Construction
Upper Garw Wetland Creation | Bridgend - Pen-yr-Bont ar Ogwr | Biodiversity and Habitat Enhancment | <50k | [9 empty] | <50k | Construction | [12 empty] | 6
Pencoed Initial Assesment | Bridgend - Pen-yr-Bont ar Ogwr | Defence | <100k | <500k | <500k | [7 empty] | <2,500k | Design | Construction | Construction | [7 empty] | TBC | TBC
Aberkenfig FAS | Bridgend - Pen-yr-Bont ar Ogwr | Defence | <50k | <100k | <500k | <1,000k | [6 empty] | <2,500k | Appraisal | Design | Construction | Construction
Maesteg Initial Assessment | Bridgend - Pen-yr-Bont ar Ogwr | Defence |  | <50k | <100k | <1,000k | [6 empty] | <2,500k |  | Appraisal | Design | Construction
Ogmore Vale Initial Assessment | Bridgend - Pen-yr-Bont ar Ogwr | Defence |  |  |  |  | <50k | <50k | <500k |  |  |  | <500k |  |  |  |  | Appraisal | Design | Construction
Aberkenfig Wall Repair | Bridgend - Pen-yr-Bont ar Ogwr | Maintenance | <50k | [9 empty] | <50k | Maintenance
Nant Brynglas Trash Screen | Bridgend - Pen-yr-Bont ar Ogwr | Maintenance | <50k | [9 empty] | <50k | Completion
Ogmore Culvert Shoal Management | Bridgend - Pen-yr-Bont ar Ogwr | Maintenance | <50k | [9 empty] | <50k | Maintenance
Coychurch Wall | Bridgend - Pen-yr-Bont ar Ogwr | Maintenance |  |  |  | <50k | <100k | [5 empty] | <100k |  |  |  | Design | Maintenance
Risca Flood Risk Management | Caerphilly - Caerffili | Defence | <5k | <5k | <5k | <5k | [6 empty] | <50k | Construction | Construction | Construction | Completion | [6 empty] | 259 | 19
Bridge St, Newbridge - New FAS | Caerphilly - Caerffili | Defence |  |  |  | <50k |  | <500k |  |  |  |  | <1000k |  |  |  | Appraisal | Design | Construction
Machen Initial Assessment | Caerphilly - Caerffili | Defence | [5 empty] | <50k | <100k | <1,000k |  |  | <2,500k |  |  |  |  | Appraisal | Design | Construction
Llanbradach IA | Caerphilly - Caerffili | Defence |  |  |  |  | <50k | <100k | <1,000k |  |  |  | <2,500k |  |  |  | Appraisal | Design | Construction
Caerphilly Tributaries IA | Caerphilly - Caerffili | Defence |  | <50k | <100k | <1,000k | [6 empty] | <2,500k |  | Appraisal | Design | Construction
Abertillery - Gabion Repairs | Caerphilly - Caerffili | Maintenance | <5k | [9 empty] | <5K | Completion
Bedwas Access Improvements | Caerphilly - Caerffili | Maintenance | <50k | [9 empty] | <50k | Completion
Ystard Mynach River Model | Caerphilly - Caerffili | Maintenance | <50k | [9 empty] | <50k | study
New Tredegar Deshoal | Caerphilly - Caerffili | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Coedypia, Ystrad Mynach - Structural Assessment | Caerphilly - Caerffili | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Appraisal
Ystrad Mynach Deshoal | Caerphilly - Caerffili | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Bedwas Walls - Structural Assessment | Caerphilly - Caerffili | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Appraisal
Roath and Rhymney Flood Risk Management | Cardiff - Caerdydd | Defence | <2,500k | <500k | <50k | [7 empty] | <2,500k | Construction | Construction | Completion | [7 empty] | 360 | 51
Llanrumney - Retreat of Defences | Cardiff - Caerdydd | Maintenance |  |  |  | <500k | [6 empty] | <500k |  |  |  | Maintenance
Cardiff FAS - Scheme Review | Cardiff - Caerdydd | Maintenance |  | <50k | <50k | <100k |  |  | <2,500k | <5,000k | <5,000k |  | >5,000k |  | Study | Appraisal | Design |  |  | Construction | Construction | Construction
Leckwith Bridge Industrial Estate | Cardiff - Caerdydd | Maintenance | <500k | [9 empty] | <500k | Maintenance | [10 empty] | 860
Caldicot and Wentlooge Sluice Improvement | Cardiff - Caerdydd | Maintenance | <50k | [9 empty] | <50k | Maintenance
Ball Road, Llanrumney | Cardiff - Caerdydd | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Cardiff Embankment Repairs (Ops Delivery) | Cardiff - Caerdydd | Maintenance |  |  | <50k | [7 empty] | <50k |  |  |  | Maintenance
Cardiff Remedial Wall Repairs (Ops Delivery) | Cardiff - Caerdydd | Maintenance |  | <50k | [8 empty] | <50k |  |  | Maintenance
Upper Ely Integrated Catchment Model | Cardiff - Caerdydd | Modelling | <50k | [9 empty] | <50k | Completion
Taff Hydrological Assessment | Cardiff - Caerdydd | Modelling | <50k | [9 empty] | <50k | study
Rhosog Fach Sea Door | Cardiff - Caerdydd | Maintenance | <50k | [9 empty] | <50k | Maintenance
Began Farm Blockstone Repairs | Cardiff - Caerdydd | Maintenance |  |  | <50k | [7 empty] | <50k | Maintenance
Melingriffith - Bank Repairs | Cardiff - Caerdydd | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Mwche Managed Realignment | Carmarthenshire - Sir Gaerfyrddin | Biodiversity and Habitat Enhancment | <500k | [9 empty] | <500k | Appraisal | [13 empty] | TBC
Pwll Flood Risk Management | Carmarthenshire - Sir Gaerfyrddin | Defence | <50k | [9 empty] | <50k | Completion
North Dafen Attenuation Pond | Carmarthenshire - Sir Gaerfyrddin | Defence | <500k | <500k | <500k | [7 empty] | <2,500k | Design | Design | Construction
Pwll Vegetation Management and Temporary Bund | Carmarthenshire - Sir Gaerfyrddin | Defence | <50k | [9 empty] | <50k | Maintenance
Johnstown FAS | Carmarthenshire - Sir Gaerfyrddin | Defence |  |  | <50k | <50k | [6 empty] | <100k |  |  | Appraisal | Design
Llanybydder FAS | Carmarthenshire - Sir Gaerfyrddin | Defence |  |  |  | <50k | <50k | <100k |  |  |  |  | <500k |  |  |  | Appraisal | Design | Construction
Ilston Flood Warning Station | Carmarthenshire - Sir Gaerfyrddin | Hydrometry & Telemetry | <50k | [9 empty] | <50k | Maintenance
Machynys Flood Defence Maintenance | Carmarthenshire - Sir Gaerfyrddin | Maintenance | <2,500k | [9 empty] | <2,500k | Maintenance
Pontyates Floodbank | Carmarthenshire - Sir Gaerfyrddin | Maintenance |  |  | <50k | <100k | [6 empty] | <500k |  |  | Maintenance | Maintenance
Drefach Felindre Flood Wall Repair | Carmarthenshire - Sir Gaerfyrddin | Maintenance | <50k | [9 empty] | <50k | Maintenance
Abergwili Access Improvements | Carmarthenshire - Sir Gaerfyrddin | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Laugharne Mill Leat De Silt | Carmarthenshire - Sir Gaerfyrddin | Maintenance |  |  | <50k | <50k | [6 empty] | <100k |  |  | Maintenance | Maintenance
Ty Castell | Carmarthenshire - Sir Gaerfyrddin | Water Resources | <50k | [9 empty] | <50k | Maintenance
Pontardawe Industrial Area Defence | Carmarthenshire - Sir Gaerfyrddin | Maintenance |  | <50k | <500k | [7 empty] | <500k |  | Appraisal | Maintenance
Llandovery Wall and Bank Improvements | Carmarthenshire - Sir Gaerfyrddin | Maintenance |  | <50k | <50k | [7 empty] | <100k |  | Maintenance | Maintenance
Llandovery | Carmarthenshire - Sir Gaerfyrddin | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Aberystwyth Wetlands | Ceredigion - Sir Ceredigion | Biodiversity and Habitat Enhancment | <50k | [9 empty] | <50k | Maintenance | [12 empty] | 4
Afon Merin re-wilding | Ceredigion - Sir Ceredigion | Biodiversity and Habitat Enhancment | <50k | [9 empty] | <50k | Construction | [12 empty] | 19
Aberystwyth Wall | Ceredigion - Sir Ceredigion | Defence | <50k | [9 empty] | <50k | Maintenance
Aberystwyth Initial Assessment | Ceredigion - Sir Ceredigion | Defence | <50k | <50k | <500k | <500k | [6 empty] | <2,500k |  | Appraisal | Design | Construction | Construction
Parc yr Onnen | Ceredigion - Sir Ceredigion | Defence | <500k | [9 empty] | <500k | Construction
Cardigan Tidal Defences | Ceredigion - Sir Ceredigion | Defence | <100k | <50k | <500k | <500k | <5,000k | <1,000k |  |  |  |  | >5,000k | Appraisal | Design | Design | Construction | Construction | Construction |  |  |  |  | TBC | TBC
Lampeter Initial Assessment | Ceredigion - Sir Ceredigion | Defence |  |  |  |  | <50k | <50k | <100k |  |  |  | <500k |  |  |  |  | Appraisal | Design | Construction
Cwmystwyth Station and Weir Refurbishment | Ceredigion - Sir Ceredigion | Hydrometry & Telemetry | <500k | [9 empty] | <500k
Clarach Coastal | Ceredigion - Sir Ceredigion | Maintenance |  |  | <50k | <500k | [6 empty] | <500k |  |  | Maintenance | Maintenance
Mwldan Overflow Outfall Improvements | Ceredigion - Sir Ceredigion | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Aberaeron | Ceredigion - Sir Ceredigion | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Borth Modelling | Ceredigion - Sir Ceredigion | Modelling |  |  |  | <50k | <50k | <100k | <1,000k |  |  |  | <2,500k |  |  |  | Appraisal | Design | Construction | Construction
Tregaron PLP | Ceredigion - Sir Ceredigion | Maintenance |  | <50k | [8 empty] | <50k | Completion
Glanyrafon Defences | Ceredigion - Sir Ceredigion | Maintenance |  |  |  | <50k | <50k | [5 empty] | <50k |  |  |  | Maintenance | Maintenance
Ffos Glanwern Timber Revetment Repairs | Ceredigion - Sir Ceredigion | Maintenance | <50k | [9 empty] | <50k | Maintenance
Dyffryn Conwy Flood Risk Management | Conwy - Conwy | Defence | <50k | [9 empty] | <50k | Maintenance
Llanfair Talhaiarn Phase 3 | Conwy - Conwy | Defence | <1,000k | <50k | [8 empty] | <1000k | Construction | Construction | [8 empty] | 29 | 4 | TBC
Mochdre Initial Assessment | Conwy - Conwy | Defence |  |  |  | <50k | [6 empty] | <50k |  |  |  | Appraisal
Pont Robin Tidal Outfall Refurbishment | Conwy - Conwy | Maintenance | <500k | <5k | [8 empty] | <500k | Construction | Completion
Tanlan Embankment Viablity Study | Conwy - Conwy | Maintenance |  | <50k | <100k | <500k | <1,000k | [5 empty] | <2,500k |  | Appraisal | Design | Construction | Construction
Afon Wydden Spillway Works | Conwy - Conwy | Maintenance | <500k | [9 empty] | <500k | Maintenance
Afon Wydden Flood Risk Mapping Study | Conwy - Conwy | Modelling | <5k | [9 empty] | <5K | Maintenance
Afon Conwy Stone Frontage Repair | Conwy - Conwy | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Belgrano & Clwyd Pump Station Review | Conwy - Conwy | Maintenance |  | <50k | <50k | <50k | <500k | [5 empty] | <500k |  | Study | Appraisal | Design | Construction
Llandudno (incl Penrhyn Bay and Rhos On Sea) - Tidal Flood Risk Modelling | Conwy - Conwy | Maintenance |  |  | <50k | [7 empty] | <50k |  |  |  | study
Ysgol Glan Morfa Embankment Refurbishment | Conwy - Conwy | Maintenance |  |  | <5k | <50k | [6 empty] | <50k |  |  |  | Maintenance | Maintenance
Dyserth IA | Denbighshire - Sir Ddinbych | Defence | <50k | [9 empty] | <50k | Study
Dyserth | Denbighshire - Sir Ddinbych | Defence |  |  |  | <50k | <50k | <100k | <2,500k |  |  |  | <2,500k |  |  |  | Appraisal | Design | Maintenance
Rhyl Sluice | Denbighshire - Sir Ddinbych | Maintenance | <5k | [9 empty] | <5K | Maintenance
Rhyl Cut Access Improvements | Denbighshire - Sir Ddinbych | Maintenance | <50k | [9 empty] | <50k | Maintenance
Warren Drive Trash screen | Denbighshire - Sir Ddinbych | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
St Asaph FCRM | Denbighshire - Sir Ddinbych | Modelling | <100k | <50k | <5k | <5k | <5k | [5 empty] | <500k | Construction | Completion | Completion | Completion | Completion | [5 empty] | 293 | 121
Rhyl Cut & Prestatyn Gutter Fluvial Modelling | Denbighshire - Sir Ddinbych | Modelling | <50k | [9 empty] | <50k | Study
Dyffryn Meadows Ind Est IA | Denbighshire - Sir Ddinbych | Defence |  |  |  | <50k | <100k | <500k |  |  |  |  | <1000k |  |  |  | Appraisal | Design | Construction
Rhyl & Gronannt Pump Station Review | Denbighshire - Sir Ddinbych | Maintenance |  | <50k | <50k | <500k | [6 empty] | <500k |  | Study | Appraisal | Construction
Tidal Clwyd FRMS Review 2017 | Denbighshire - Sir Ddinbych | Maintenance | <500k | <500k | <5,000k | <5,000k | <2,500K | <5,000k | <2,500k | <5,000k | <5,000k | <5,000k | >5,000k | Appraisal | Design | Construction | Construction | Construction | Construction | Construction | Construction | Construction | Construction
Glanfyddion Sluice | Denbighshire - Sir Ddinbych | Maintenance | <1,000k | <5k | [8 empty] | <1000k | Construction | Completion
Ffynnon y Ddol Culvert Works | Denbighshire - Sir Ddinbych | Maintenance |  |  |  | <50k | <50k | [5 empty] | <50k |  |  |  | Maintenance | Maintenance
Greenfield Marsh Tidal Embankment | Flintshire - Sir y Fflint | Maintenance | <100k | <100k | <1,000k | <1,000k | [6 empty] | <2,500k | Appraisal | Construction | Construction
Work arising from the Dee strategy | Flintshire - Sir y Fflint | Maintenance |  | <50k | <500k | <500k | <500k | <1,000k | <5,000k | <5,000k | <5,000k | >5,000k | >5,000k |  | Appraisal | Design | Construction | Construction | Construction | Construction | Construction | Construction | Construction
Wepre Gutter Pilling Works | Flintshire - Sir y Fflint | Maintenance | <500k | <500k | [8 empty] | <500k | Construction | Construction
Rowleys Pumping Station Weedscreen | Flintshire - Sir y Fflint | Maintenance | <50k | [9 empty] | <50k | Maintenance
Higherferry Queensferry & Rowleys Pump Station Review | Flintshire - Sir y Fflint | Maintenance |  | <50k | <50k | <50k | <50k | <500k |  |  |  |  | <500k |  | Study | Appraisal | Design | Construction | Construction
Broughton Brook & Queensferry Drain Modelling Study | Flintshire - Sir y Fflint | Modelling |  | <5k | <50k | [7 empty] | <50k |  | Study | Study
Sealand - Northern Embankment Slump | Flintshire - Sir y Fflint | Maintenance |  | <50k | <100k | [7 empty] | <500k |  | Design | Maintenance
Gele Sluice | Flintshire - Sir y Fflint | Maintenance | <500k | <2,500k | <5k | [7 empty] | <2,500k | Construction | Construction | Completion
Point of Ayr | Flintshire - Sir y Fflint | Maintenance | <500k | <500k | <5k | [7 empty] | <500k | Construction | Construction | Completion
Llong Floodgate | Flintshire - Sir y Fflint | Maintenance | <50k | [9 empty] | <50k | Maintenance
Talacre Pumping Station Efficiency Improvements | Flintshire - Sir y Fflint | Maintenance |  | <5k | <5k | <100k | [6 empty] | <100k |  | Appraisal | Appraisal | Construction
Graig Lane Pumping Station Efficiency Improvements | Flintshire - Sir y Fflint | Maintenance |  | <5k | <5k | <100k | [6 empty] | <100k |  | Appraisal | Appraisal | Construction
Bodoryn & Gypsey Lane Pump Station Review | Flintshire - Sir y Fflint | Maintenance |  | <50k | <50k | <500k | [6 empty] | <500k |  | Appraisal | Appraisal | Construction
Sealand & Thornleigh Pump Station Review | Flintshire - Sir y Fflint | Maintenance |  | <50k | <50k | <50k | <100k | [5 empty] | <500k |  | Appraisal | Appraisal | Design | Construction
Bretten Initial Assessment | Flintshire - Sir y Fflint | Defence |  |  |  | <50k | [6 empty] | <50k |  |  |  | Appraisal
Beeches Drain Outfall | Flintshire - Sir y Fflint | Maintenance |  |  | <50k | <50k | [6 empty] | <100k |  |  |  | Maintenance | Maintenance
Balderton Pump Station Review | Flintshire - Sir y Fflint | Maintenance |  | <5k | <5k | <100k | [6 empty] | <500k |  | Appraisal | Appraisal | Construction
Thornleigh PS Bank Stabalisation | Flintshire - Sir y Fflint | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Fairbourne Flood Risk Management Scheme | Gwynedd - Gwynedd | Defence | <500k | [9 empty] | <500k | Construction | [9 empty] | 410 | 10
Dolgellau (Wnion and Arran) Flood Risk Management | Gwynedd - Gwynedd | Defence | <5k | <5k | <5k | <5k | [6 empty] | <50k | Completion | Completion | Completion | Completion
Llyn Tegid Reservoir Safety Works | Gwynedd - Gwynedd | Defence | <1,000k | <5,000k | <5,000k | [7 empty] | >5,000k | Design | Construction | Construction
Garndolbenmaen Gauging Station | Gwynedd - Gwynedd | Hydrometry & Telemetry | <50k | <5k | [8 empty] | <50k | Construction | Completion
Ffriog Cliffs Sea Defence Repairs | Gwynedd - Gwynedd | Maintenance | <2,500k | [9 empty] | <2,500k | Construction
Porthmadog Tidal Structures | Gwynedd - Gwynedd | Maintenance | <100k | <100k | <500k | <1,000k | [6 empty] | <2,500k | design | Construction | Construction | Construction
Bangor on Dee Embankment Slippage | Gwynedd - Gwynedd | Maintenance |  | <50k | <50k | <50k | <1,000k | <500k |  |  |  |  | <2,500k |  | design | Maintenance | Maintenance | Maintenance | Maintenance
Llandanwg Breakwater | Gwynedd - Gwynedd | Maintenance |  |  |  | <50k | <50k | [5 empty] | <100k |  |  |  | Maintenance | Maintenance
Dinas Dinlle Strategy | Gwynedd - Gwynedd | Maintenance |  | <50k | <100k | <500k | <1,000k | [5 empty] | <2,500k |  | Appraisal | Design | Construction | Construction
Afon Rhyd Hir | Gwynedd - Gwynedd | Maintenance |  |  |  | <100k | <100k | <1,000k |  |  |  |  | <2,500k |  |  | Appraisal | Design | Construction
Drefach Llanybydder Flood Defence Repairs | Gwynedd - Gwynedd | Maintenance | <50k | [9 empty] | <50k | Maintenance
White Barn North - Culvert Replacement | Gwynedd - Gwynedd | Maintenance | <100k | [9 empty] | <100k | Maintenance
Draenogau Tidal Doors | Gwynedd - Gwynedd | Maintenance | <50k | [9 empty] | <50k | Maintenance
CWRT Chamber & Weedscreen | Gwynedd - Gwynedd | Maintenance |  |  | <50k | <50k | [6 empty] | <50k |  |  | Maintenance | Maintenance
Abererch Dunes Sheet Piling Refurbishment | Gwynedd - Gwynedd | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Penllyn Tywyn Outfall | Gwynedd - Gwynedd | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Afon Seiont Hydraulic Modeling | Gwynedd - Gwynedd | Modelling | <50k | [9 empty] | <50k | Study
South Tremadog Bay Communities Tidal FRA | Gwynedd - Gwynedd | Modelling | <100k | [9 empty] | <100k | Study
Ty Gwyn Tidal Door Modelling | Gwynedd - Gwynedd | Modelling |  |  |  | <50k | <50k | <2,500k |  |  |  |  | <2,500k |  |  |  | Study | Design | Construction
Fairbourne & Barmouth - Tidal Flood Risk Modelling | Gwynedd - Gwynedd | Modelling |  |  |  | <50k | [6 empty] | <50k |  |  |  | Study
Bala Sluice Auto Upgrade 2017 | Gwynedd - Gwynedd | Maintenance | <500k | [9 empty] | <500k | Other
Aberech Bank Reprofile | Gwynedd - Gwynedd | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Mochras Flood Bank and Tidal Door | Gwynedd - Gwynedd | Maintenance |  |  |  | <50k | <50k | <1,000k | <2,500k |  |  |  | <5,000k |  |  |  | Appraisal | Design | Construction | Construction
Maes y Ffynnon Wall Refurbishment | Gwynedd - Gwynedd | Maintenance |  |  | <50k | <100k | [6 empty] | <100k |  |  | Maintenance | Maintenance
Afon Bodfan Outfall Improvements | Gwynedd - Gwynedd | Maintenance | <50k | [9 empty] | <50k | Maintenance
Valley | Isle of Anglesey - Sir Ynys Mon | Maintenance |  |  | <50k | <50k | <100k | <500k | <1,000k |  |  |  | <2,500k |  |  | study | Appraisal | Design | Construction | Construction
Afon Gwyrfai Flood Risk Study | Isle of Anglesey - Sir Ynys Mon | Modelling | <50k | <100k | [8 empty] | <500k | Study | Study
Dwyran Flood Risk Study | Isle of Anglesey - Sir Ynys Mon | Modelling | <50k | <50k | <100k | <500k | [6 empty] | <1000k | Study | Appraisal | Design | Construction
Llangefni Flood Risk Study | Isle of Anglesey - Sir Ynys Mon | Modelling | <50k | <50k | <100k | <500k | [6 empty] | <1000k | Study | Appraisal | Design | Construction
Malltraeth Tidal Doors Replacement | Isle of Anglesey - Sir Ynys Mon | Maintenance |  |  |  | <100k | [6 empty] | <100k |  |  |  | Maintenance
Amlwch | Isle of Anglesey - Sir Ynys Mon | Maintenance | [5 empty] | <100k | <500k |  |  |  | <1000k | [5 empty] | Maintenance | Maintenance
Troedyrhiw - New FAS [RB] | Merthyr Tydfil - Merthyr Tudful | Defence | [7 empty] | <500k | <2,500k |  | <2,500k | [7 empty] | Construction | Construction
Portland Grounds Sea Defence Improvement | Monmouthshire - Sir Fynwy | Maintenance | <50k | [9 empty] | <50k | Construction
Tafalog Gauging Station | Monmouthshire - Sir Fynwy | Maintenance | <5k | <500k | [8 empty] | <500k |  | Design | construction
Monmouth Flood Gates - Improvements | Monmouthshire - Sir Fynwy | Maintenance |  | <50k | <100k | <500k | [6 empty] | <1000k |  |  | Design | Design | Maintenance
Sudbrook/Chepstow - Sea Defence Improvements | Monmouthshire - Sir Fynwy | Maintenance | <100k | <500k | <500k | <1,000k | [6 empty] | <2,500k | Appraisal | Design | Construction | Construction | [6 empty] | TBC | TBC
Redbrook Gauging Station Refurbishment | Monmouthshire - Sir Fynwy | Maintenance | <5k | [9 empty] | <5K | Maintenance
Monmouth FAS – Embankment Repair | Monmouthshire - Sir Fynwy | Maintenance | <100k | [9 empty] | <100k | Maintenance
Sea Doors - Asset Replacement Study | Monmouthshire - Sir Fynwy | Maintenance | <50k | [9 empty] | <50k | Maintenance
Leys to Mathern Access | Monmouthshire - Sir Fynwy | Maintenance | <50k | [9 empty] | <50k | Maintenance
West Pill Outfall Improvments | Monmouthshire - Sir Fynwy | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Chepstow FAS - Gate Replacement | Monmouthshire - Sir Fynwy | Maintenance | <5k | [9 empty] | <5k | Maintenance
Ffrwd Wyllt SMNR | Neath Port Talbot - Castell-nedd Port Talbot | Biodiversity and Habitat Enhancment | <50k | <50k | [8 empty] | <50k | Other | Other | [11 empty] | 3
Resolven Aqueduct Improvements | Neath Port Talbot - Castell-nedd Port Talbot | Defence |  |  |  | <100k | [6 empty] | <100k |  |  |  | Construction
Ffrwd Wyllt Fluvial Initial Assessment | Neath Port Talbot - Castell-nedd Port Talbot | Defence |  |  | <50k | <100k | <500k | <1,000k |  |  |  |  | <2,500k |  |  | Appraisal | Design | Construction
Cwmafan Initial Assessment | Neath Port Talbot - Castell-nedd Port Talbot | Defence | <50k | <500k | <500k | [7 empty] | <500k | Appraisal | Design | Construction
Margam Initial Assessment | Neath Port Talbot - Castell-nedd Port Talbot | Defence |  |  |  | <50k | <50k | [5 empty] | <100k |  |  |  | Study | Appraisal
Cadoxton Neath Initial Assessment | Neath Port Talbot - Castell-nedd Port Talbot | Defence | [5 empty] | <50k | <500k | <500k | <1,000k |  | <2,500k | [5 empty] | Appraisal | Design | Construction
Neath Abbey IA | Neath Port Talbot - Castell-nedd Port Talbot | Defence |  |  |  | <50k | [6 empty] | <50k |  |  |  | Study | [8 empty] | TBC
Cwm Clydach Dam Repairs | Neath Port Talbot - Castell-nedd Port Talbot | Maintenance | <500k | [9 empty] | <500k | Maintenance
Port Talbot Gravel Removal | Neath Port Talbot - Castell-nedd Port Talbot | Maintenance | <50k | [9 empty] | <50k | Maintenance
Resolven Weir Refurbishment | Neath Port Talbot - Castell-nedd Port Talbot | Maintenance | <50k | <5k | [8 empty] | <50k | Maintenance | Maintenance
Cilfrew Weir Refurbishment | Neath Port Talbot - Castell-nedd Port Talbot | Maintenance | <5k | [9 empty] | <5k | Maintenance
Glynneath FAS Capital Maintenance | Neath Port Talbot - Castell-nedd Port Talbot | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Aberdulais Evacuation Plan Reviews | Neath Port Talbot - Castell-nedd Port Talbot | Maintenance |  | <50k | [8 empty] | <50k |  | Study
Caldicot and Wentlooge Model Update | Neath Port Talbot - Castell-nedd Port Talbot | Modelling | <5k | [9 empty] | <5K | Study
Riverside Newport Flood Risk Management | Newport - Casnewydd | Defence | <50k | [9 empty] | <50k | Construction
Crindau Pill Flood Risk Management Improvements | Newport - Casnewydd | Defence | <2,500k | <1,000k | <500k | <50k | <5k | [5 empty] | <5,000k | Construction | Construction | Construction | Construction | Completion | [5 empty] | 549 | 118
Home Farm, Caerleon - New FAS | Newport - Casnewydd | Defence |  |  |  | <100k | [6 empty] | <100k |  |  |  | Appraisal
Tabbs Gout Sea Defence Improvements | Newport - Casnewydd | Maintenance | <50k | [9 empty] | <50k | Construction | [9 empty] | 570 | 180
Stephenson Street, Liswerry | Newport - Casnewydd | Maintenance | <500k | <5,000k | <100k |  | <50k | <500k |  |  |  |  | >5,000k | Design | Construction | Construction |  | Construction | Construction
Selwyns Door - Culvert Replacement | Newport - Casnewydd | Maintenance | <50k | [9 empty] | <50k | Maintenance
Julians Reen Access Improvements and Wing Wall Repair | Newport - Casnewydd | Maintenance | <50k | [9 empty] | <50k | Maintenance
Riverside Newport - 90s Wall [Structural Assessment] | Newport - Casnewydd | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Tredegar Park Shoal Removal | Newport - Casnewydd | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance | [8 empty] | TBC
Back Ditch | Newport - Casnewydd | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Liswery Pill Model Update | Newport - Casnewydd | Modelling | <50k | [9 empty] | <50k | Study
NHCP Projects | Other | Biodiversity and Habitat Enhancment | <500k | <2,500k | <2,500k | <2,500k | <2,500K | <2,500k | <2,500k | <2,500k | <2,500k | <2,500k | >5,000k | other | other | other | other | other | other | other | other | other | other |  |  |  |  | TBC
Transport and Plant Hydrometry (Contribution) | Other | Fleet | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <500k | other | other | other | other | other | other | other | other | other | other
Wales FCRM Fleet Asset Replacement Programme | Other | Fleet | <1,000k | <1,000k | <500k | <1,000k | <1,000k | <1,000k | <1,000k | <1,000k | <1,000k | <500k | >5,000k | other | other | other | other | other | other | other | other | other | other
FRM Transformation - Telemetry Strategy | Other | Hydrometry & Telemetry | <500k | <500k | <500k | [7 empty] | <1000k | other | other | other | other | other | other | other | other | other | other
FRM Transformation - NaFRA Replacement Product | Other | ICT | <1,000k | [9 empty] | <1000k | Study
FRM Transformation - Software Purchases | Other | ICT | <50k | [9 empty] | <50k
FRM Transformation Programme | Other | ICT | <1,000k | [9 empty] | <1000k | Other
Capital Maintenance Ops Delivery South East | Other | Maintenance |  |  |  |  | <500k | <500k | <500k | <500k | <500k | <500k | <1000k |  |  |  |  | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance
Capital Maintenance Ops Delivery South West | Other | Maintenance |  |  |  |  | <500k | <500k | <500k | <500k | <500k | <500k | <1000k |  |  |  |  | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance
Capital Maintenance Ops Delivery North | Other | Maintenance |  |  |  |  | <500k | <500k | <500k | <500k | <500k | <500k | <2,500k |  |  |  |  | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance | Maintenance
Wales FCRM Fleet Asset Replacement Programme 17/18 | Other | Maintenance | <500k | [9 empty] | <500k | Other
CCTV Culvert Surveys SW | Other | Maintenance | <5k | [9 empty] | <5K | Maintenance
SW Access Areas | Other | Maintenance | <5k | [9 empty] | <5K | Maintenance
Wales FCRM Fleet Asset Replacement Programme 16/17 | Other | Maintenance | <50k | [9 empty] | <50k | Other
MEICA Asset Management Systems | Other | Maintenance |  | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <500k |  | Other | Other | Other | Other | Other | Other | Other | Other | Other
Northern Area Pumping Station Review - Phase 4A | Other | Maintenance | <5k | <5k | <5k | <500k | [6 empty] | <500k | Appraisal | Appraisal | Appraisal | Construction
Northen Area - Topographic Survey Requirements | Other | Maintenance | <50k | <50k | <50k | [7 empty] | <50k | Study | Study | Study
Landscape Maintenance | Other | Maintenance | <50k | <5k | <50k | [7 empty] | <50k | Maintenance | Maintenance | Maintenance | [9 empty] | TBC
Culvert CCTV Survey Programme | Other | Maintenance | <50k | [9 empty] | <50k | Maintenance
Public Safety Improvements 2018/19 | Other | Maintenance | <50k | [9 empty] | <50k
North Wales Culvert Inspection and Maintenance | Other | Maintenance | <50k | [9 empty] | <50k | Maintenance
Culverts Moving Forward Project | Other | Maintenance |  |  | <50k | <50k | <50k | [5 empty] | <100k |  |  | Maintenance | Maintenance | Maintenance
Sea Outfall Maintenance Appraisal | Other | Maintenance |  |  |  | <500k | [6 empty] | <500k |  |  |  | Maintenance
3rd Party Assets Strategy | Other | Maintenance |  | <50k | [8 empty] | <50k |  | Study
Northern Area Pumping Station Review | Other | Modelling | <5k | <100k | [8 empty] | <500k | Study | Study
Reservoir Flood Designation Mapping 2017 | Other | Modelling | <500k | <1,000k | [8 empty] | <2,500k | Study | Study
Replacement Flood Risk Asset Management System | Other | Modelling | <100k | [9 empty] | <100k | other
NE Wales Tidal Defences Survey | Other | Modelling | <5k | <5k | <5k | [7 empty] | <50k | Study | Study | Study
SE Topo Data Collection | Other | Modelling | <50k | [9 empty] | <50k | Study
Northern Area Mapping | Other | Modelling |  |  |  |  | <100k | <100k | <100k | <100k | <100k | <100k | <1000k |  |  |  |  | Study | Study | Study | Study | Study | Study
South East Area Mapping Projects | Other | Modelling |  |  |  |  | <100k | <100k | <100k | <100k | <100k | <100k | <1000k |  |  |  |  | Study | Study | Study | Study | Study | Study
South West Area Mapping projects | Other | Modelling |  |  |  |  | <100k | <100k | <100k | <100k | <100k | <100k | <1000k |  |  |  |  | Study | Study | Study | Study | Study | Study
Flood Forecasting Hydrometric Improvements | Other | Other | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <50k | <500k | other | other | other | other | other | other | other | other | other | other
Wales FRM Capital Sals (EAW) | Other | Salaries | <2,500k | <2,500k | <2,500k | <2,500k | <2,500K | <2,500k | <2,500k | <2,500k | <2,500k | <2,500k | >5,000k | other | other | other | other | other | other | other | other | other | other
Dyfi Valley FWS Review | Other | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Upper Dee FWS Review | Other | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Lower Dee FWS Review | Other | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Solva Catchment NFRM Project | Pembrokeshire - Sir Benfro | Biodiversity and Habitat Enhancment | <50k | <50k | [8 empty] | <50k | Construction | [12 empty] | 2
Haverfordwest Defences | Pembrokeshire - Sir Benfro | Defence |  |  |  | <50k | <500k | <500k | <2,500k |  |  |  | <2,500k |  |  |  | Appraisal | Design | Construction | Construction
Cilrhedyn Bridge | Pembrokeshire - Sir Benfro | Hydrometry & Telemetry | <5k | [9 empty] | <5k | Maintenance
Pont y Cerbyd Reservoir Section 10 | Pembrokeshire - Sir Benfro | Maintenance | <500k | [9 empty] | <500k | Maintenance
Pont y Cerbyd Access Improvements | Pembrokeshire - Sir Benfro | Maintenance | <5k | [9 empty] | <5K | Maintenance
Tenby Buoy Assessment | Pembrokeshire - Sir Benfro | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Ritec Culvert Improvements | Pembrokeshire - Sir Benfro | Maintenance |  | <100k | [8 empty] | <100k |  | Maintenance
Little Haven | Pembrokeshire - Sir Benfro | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Tenby Access | Pembrokeshire - Sir Benfro | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Stepaside Defences | Pembrokeshire - Sir Benfro | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Ystradgynlais Flood Risk Management | Powys - Powys | Defence | <50k | [9 empty] | <50k | Maintenance
Crickhowell IA | Powys - Powys | Defence | [6 empty] | <50k | <100k | <1,000k |  | <2,500k | [6 empty] | Appraisal | Design | Construction
Llanidloes Initial Assessment | Powys - Powys | Defence |  |  | <50k | [7 empty] | <50k |  |  | Study
Esgair Carnau - Bank Protection | Powys - Powys | Hydrometry & Telemetry | <500k | <5k | [8 empty] | <500k | construction | Completion
Llys Tawel Wall, Ystradgynlais | Powys - Powys | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | construction
Brecon Embankment Repairs and Deshoal | Powys - Powys | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Glasbury - Structural Assessment | Powys - Powys | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Llanwrytyd Wells | Powys - Powys | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Disserth Gauging Station | Powys - Powys | Water Resources | <50k | <500k | [8 empty] | <1000k | Maintenance | Maintenance
Trehelig Door and Argae Refurbishment | Powys - Powys | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Gwydderig Blockstone | Powys - Powys | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Builth Road Floodbank Repair | Powys - Powys | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Hirwaun - New FAS | Rhondda Cynon Taf - Rhondda Cynon Taf | Defence |  | <50k | <100k | <500k | [6 empty] | <1000k |  | Appraisal | Design | Construction
Robertstown IA | Rhondda Cynon Taf - Rhondda Cynon Taf | Defence |  |  |  |  | <50k | <100k | <1,000k | <2,500k |  |  | <5,000k |  |  |  |  | Study | Appraisal | Design | Construction
Glyntaff Initial Assessment | Rhondda Cynon Taf - Rhondda Cynon Taf | Defence |  |  |  | <50k | [6 empty] | <50k |  |  |  | Study
Pontyclun Initial Assessment | Rhondda Cynon Taf - Rhondda Cynon Taf | Defence |  | <50k | [8 empty] | <50k |  | Study
Llwynypia Wall Repair | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance | <100k | [9 empty] | <100k | Design | [9 empty] | 55
River Rhondda Asset Management Plan | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  | <50k | <100k | <500k | <1,000k | [5 empty] | <2,500k | Appraisal | Appraisal | Design | Construction
Treforest Ind Est - Structural Assessment | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  | <50k | <50k | <500k | <1,000k | <1,000k |  |  |  |  | <2,500k | Appraisal | Appraisal | Design | Construction
Mountain Ash - Phase 2 | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  | <50k | <50k | [6 empty] | <100k |  |  | Maintenance | Maintenance
Nant Aman Culvert Screen | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Trehafod Blockstone Repairs | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Ynysddu - Structural Assessment | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Treforest Deshoal | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Pontyclun Deshoal | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Rhondda Confluence | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  | <50k | [8 empty] | <50k |  | Maintenance
Porth/Hopkinstown Wall Repairs | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  |  |  | <50k | [5 empty] | <50k | [5 empty] | Maintenance
Aberdare Culvert Inspections | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  |  | <5k | [7 empty] | <5k |  |  | Maintenance
Afon Cynon Integrated Catchment Model | Rhondda Cynon Taf - Rhondda Cynon Taf | Modelling | <50k | [9 empty] | <50k | Study
Assessment of NFM Impacts in the Rhondda Valley | Rhondda Cynon Taf - Rhondda Cynon Taf | Maintenance |  | <50k | [8 empty] | <50k |  | Study
Cwm Ivy Marsh Managed Realignment | Swansea - Abertawe | Biodiversity and Habitat Enhancment | <50k | <50k | <50k | [7 empty] | <50k | Other | Other | Other
Ammanford FAS | Swansea - Abertawe | Defence | <500k | <500k | <500k | <500k | [6 empty] | <2,500k | Design | Construction | Construction | Construction | [6 empty] | TBC | TBC
Pontarddulais Flood Risk Management | Swansea - Abertawe | Defence | <500k | [9 empty] | <500k | Construction | [9 empty] | 224 | 22
Gorseinon FAS | Swansea - Abertawe | Defence |  |  |  | <50k | <100k | [5 empty] | <100k |  |  |  | Appraisal | Design
Llansamlet Initial Assessment | Swansea - Abertawe | Defence |  |  |  | <50k | <50k | <500k |  |  |  |  | <500k |  |  |  | Study | Appraisal | Design
Ynystanglws Bank Wall Improvements | Swansea - Abertawe | Hydrometry & Telemetry | <5k | [9 empty] | <5K | Maintenance
Ynystawe Park Floodbank Repair | Swansea - Abertawe | Maintenance | <50k | [9 empty] | <50k | Maintenance | [11 empty] | TBC
Crynant Post Event Remedial Work | Swansea - Abertawe | Maintenance |  | <100k | [8 empty] | <100k |  | Maintenance
Loughor Flood Bank Repairs | Swansea - Abertawe | Maintenance |  |  | <50k | <50k | [6 empty] | <100k |  |  | Maintenance | Maintenance
Crofty River Channel Improvements | Swansea - Abertawe | Maintenance |  |  |  | <50k | <50k | [5 empty] | <100k |  |  |  | Maintenance | Maintenance
Trebanos Floodbank | Swansea - Abertawe | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Maintenance
Clydach Flood Risk Mapping Study | Swansea - Abertawe | Modelling |  |  | <50k | [7 empty] | <50k |  |  | Study
Nant y Fedrod Access | Swansea - Abertawe | Maintenance |  |  | <50k | [7 empty] | <50k |  |  | Maintenance
Contribution to Coldbrook FAS | The Vale of Glamorgan - Bro Morgannwg | Defence | <50k | [9 empty] | <50k | Other
River Cadaxton Improvements | The Vale of Glamorgan - Bro Morgannwg | Defence | <2,500k | <5,000k | [8 empty] | >5,000k | Construction | Construction | [8 empty] | 194 | 24
Cadoxton Sea Door Improvements | The Vale of Glamorgan - Bro Morgannwg | Maintenance | <2,500k | [9 empty] | <2,500k | Maintenance | [9 empty] | 12 | 80
Llanyrafon, Cwmbran - Improve FAS | Torfaen - Tor-faen | Maintenance |  | <50k | <100k | <500k | <500k | <100k |  |  |  |  | <2,500k |  | Appraisal | Design | Maintenance | Maintenance | Maintenance
Ponthir - Structural Assessment | Torfaen - Tor-faen | Maintenance |  |  |  | <50k | [6 empty] | <50k |  |  |  | Appraisal
Afon Llwyd Integrated Catchment Model | Torfaen - Tor-faen | Modelling | <5k | [9 empty] | <5K | Study
Bangor on Dee Embankment | Wrexham - Wrecsam | Defence | <50k | [9 empty] | <50k | Maintenance
Trevalyn Pumping Station Review | Wrexham - Wrecsam | Maintenance |  | <50k | <5k | <5k | <5k | <100k |  |  |  |  | <500k |  | Study | Appraisal | Appraisal | Appraisal | Construction