## Appendix 1
Flood Risk Management Advisory Group 11th January 2019
Capital Programme Update 2018/19
Appendix 1 - Future Investment Programme Ten Year Proposal
FRMW Capital Investment Programme
|  | 2018/19 Yr 0 (£) | 2019/20 Yr 1 (£) | 2020/21 Yr 2 (£) | 2021/22 Yr 3 (£) | 2022/23 Yr 4 (£) | 2023/24 Yr 5 (£) | 2024/25 Yr 6 (£) | 2025/26 Yr 7 (£) | 2026/27 Yr 8 (£) | 2027/28 Yr 9+ (£)
Programme Value |  | 18239179.99 | 18108829.9655 | 23879909.58 | 18460792.51 | 21060027 | 23213000 | 22750000 | 26070000 | 28070000 | 143070000
Budget |  | 19984607 | 18000000 | 18000000 | 18000000 | 18000000 | 18000000 | 18000000 | 18000000 | 18000000 | n/a
Over-programme |  | -1745427.01 | 108829.9655 | 5879909.58 | 460792.51 | 3060027 | 5213000 | 4750000 | 8070000 | 10070000 | n/a
Over-programme % |  | -8.734% | 0.6046% | 32.67% | 2.56% | 17% | 28.96% | 26.39% | 44.83% | 55.94% | n/a
FRMW Capital Investment Programme
Project | Total Project Cost | 2018/19 Yr 0 | 2019/20 Yr 1 | 2020/21 Yr 2 | 2021/22 Yr 3 | 2022/23 Yr 4 | 2023/24 Yr 5 | 2024/25 Yr 6 | 2025/26 Yr 7 | 2026/27 Yr 8 | 2027/28 Yr 9+ | Community Risk Register Ranking
Blaenau Gwent - Blaenau Gwent
Cwm IA | 1110000 | 0 | 0 | 0 | 0 | 10000 | 100000 | 1000000 | 0 | 0 | 0 | 52
Abertillery IA | 110000 | 0 | 0 | 10000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 60
Abertillery & Six Bells - Structural Assessment | 80000 | 0 | 0 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 60
Aberbeeg Flow Monitoring Station | 428852.75 | 886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131
Abertillery - Gabion Repairs | 33250 | 20635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60
Aberbeeg Blockstone | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131
Bridgend - Pen-yr-Bont ar Ogwr
Aberkenfig FAS | 1265000 | 0 | 0 | 15000 | 250000 | 0 | 1000000 | 0 | 0 | 0 | 0 | 177
Pencoed Initial Assesment | 850000 | 0 | 0 | 0 | 100000 | 750000 | 0 | 0 | 0 | 0 | 0 | 103
Maesteg Initial Assessment | 520000 | 0 | 0 | 20000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 46
Ogmore Vale Initial Assessment | 300000 | 0 | 0 | 0 | 0 | 50000 | 250000 | 0 | 0 | 0 | 0 | 102
Coychurch Wall | 20000 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 610
Aberkenfig Wall Repair | 17778 | 17778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177
Upper Garw Wetland Creation | 17500 | 17500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Nant Brynglas Trash Screen | 17490.7 | 10228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 601
Ogmore Culvert Shoal Management | 9000 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487
Coytrahen Blockstone Repair | 5254 | 5254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 851
Caerphilly - Caerffili
Caerphilly Tributaries IA | 1110000 | 0 | 0 | 10000 | 100000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 48
Machen Initial Assessment | 1110000 | 0 | 0 | 0 | 0 | 10000 | 100000 | 1000000 | 0 | 0 | 0 | 139
Llanbradach IA | 1110000 | 0 | 0 | 0 | 0 | 10000 | 100000 | 1000000 | 0 | 0 | 0 | 58
Bridge St, Newbridge - New FAS | 550000 | 0 | 0 | 0 | 50000 | 500000 | 0 | 0 | 0 | 0 | 0 | 189
Dyffryn Meadows Ind Est IA | 510000 | 0 | 0 | 0 | 10000 | 500000 | 0 | 0 | 0 | 0 | 0 | 40
New Tredegar Deshoal | 35000 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 273
Risca Ramps | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33
Coedypia, Ystrad Mynach - Structural Assessment | 30000 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 95
Ystrad Mynach Deshoal | 30000 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 95
Ystard Mynach River Model | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95
Bedwas Access Improvements | 11709 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151
Risca Flood Risk Management | 2412009.75 | 6822 | 2212 | 2214 | 1924 | 0 | 0 | 0 | 0 | 0 | 0 | 33
Cardiff - Caerdydd
Cardiff FAS - Scheme Review | 5020000 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 2000000 | 3000000 | 0 | 1
Leckwith Bridge Industrial Estate | 823355.93 | 87953 | 427000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
Llanrumney - Retreat of Defences | 250000 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 39
Rhosog Fach Sea Door | 45000 | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90
Rhosog Fach Sea Door Modification | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90
Melingriffith - Bank Repairs | 25000 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379
Began Farm Blockstone Repairs | 25000 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457
Ball Road, Llanrumney | 25000 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 39
Cardiff Remedial Wall Repairs (Ops Delivery) | 20000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137
Cardiff Embankment Repairs (Ops Delivery) | 20000 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 137
Roath and Rhymney Flood Risk Management | 11623635.21 | 1950416 | 705600 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17
Carmarthenshire - Sir Gaerfyrddin
Pwll Flood Risk Management | 1962583.77 | 12100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34
North Dafen Attenuation Pond | 1537428.54 | 78448 | 100000 | 0 | 300000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 23
Ammanford FAS | 987289.52 | 121045 | 150000 | 500000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 78
Mwche Managed Realignment | 232565.12 | 27558 | 195000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Machynys Flood Defence Maintenance | 1171606.17 | 1112304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23
Llanybydder FAS | 115000 | 0 | 0 | 0 | 15000 | 100000 | 0 | 0 | 0 | 0 | 0 | 219
Llandovery Wall and Bank Improvements | 80000 | 0 | 0 | 30000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 83
Johnstown FAS | 60000 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 159
Laugharne Mill Leat De Silt | 55000 | 0 | 0 | 25000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 374
Bawddwr Flood Bank Repair | 53152 | 29211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78
Pwll Vegetation Management and Temporary Bund | 40143 | 21500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34
Llandovery | 37500 | 0 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162
Llanelli Mapping Study | 35000 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23
Pontyates Floodbank | 30956 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 655
Abergwili Incident Response Road Signs | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 458
Gwydderig Blockstone | 20000 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 78
St Clears Mapping Study | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459
Hendy Flood Risk Mapping Study | 18450 | 18450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246
Builth Road Floodbank Repair | 12000 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78
Ty Castell | 10318.62 | 10259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160
Ilston Flood Warning Station | 9109.6 | 7961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 835
Drefach Felindre Flood Wall Repair | 8550 | 8550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 507
Drefach Llanybydder Flood Defence Repairs | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1122
Cwm Waun Gron Soft Engineering Repair | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240
Ceredigion - Sir Ceredigion
Cardigan Tidal Defences | 6712511.56 | 0 | 100000 | 50000 | 500000 | 1000000 | 4000000 | 1000000 | 0 | 0 | 0 | 206
Aberystwyth Initial Assessment | 3130000 | 0 | 0 | 30000 | 100000 | 3000000 | 0 | 0 | 0 | 0 | 0 | 70
Clarach Coastal | 170000 | 0 | 0 | 20000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 532
Lampeter Initial Assessment | 125000 | 0 | 0 | 0 | 0 | 25000 | 100000 | 0 | 0 | 0 | 0 | 226
Parc yr Onnen | 251773 | 138136 | 101666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70
Mwldan Overflow Outfall Improvements | 40000 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199
Aberaeron | 30000 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 261
Afon Merin re-wilding | 26950 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Aberystwyth Wetlands | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Tregaron Mapping Study | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 397
Llanbadarn Flood Bank Vegetation Clearance | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69
Tregaron PLP | 10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 389
Aberystwyth Wall | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70
Clarach Bay Flood Bank Repair | 1540 | 1540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 686
Cwmystwyth Station and Weir Refurbishment | 112226.015 | 77461 | 4033.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69
Conwy - Conwy
Tan lan Embankment Viablity Study | 4010811 | 49811 | 411000 | 50000 | 0 | 500000 | 3000000 | 0 | 0 | 0 | 0 | 93
Gele Sluice | 1174172.83 | 2056 | 52000 | 716100 | 399100 | 3000 | 0 | 0 | 0 | 0 | 0 | 9
Dyffryn Conwy Flood Risk Management | 8170520.45 | 53147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93
Afon Wydden Spillway Works | 235273 | 25000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
Llandudno (incl Penrhyn Bay and Rhos On Sea) - Tidal Flood Risk Modelling | 50000 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 5
Llanfair Talhaiarn Phase 3 | 1968769 | 919292 | 716803 | 31000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372
Bryn Engan Embankment Breach | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 553
Afon Ganol Bifurcation Refubishment | 16500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93
Afon Wydden Flood Risk Mapping Study | 15520 | 2180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
Mochdre Initial Assessment | 10000 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 94
White Barn North - Culvert Replacement | 307120.59 | 125572 | 174050 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308
Denbighshire - Sir Ddinbych
Tidal Clwyd FRMS | 97581920 | 6790 | 50000 | 100000 | 100000 | 300000 | 2000000 | 5000000 | 10000000 | 10000000 | 70000000 | 3
Dyserth Initial Assessment | 1400000 | 0 | 0 | 0 | 50000 | 50000 | 100000 | 1200000 | 0 | 0 | 0 | 230
Glanfyddion Sluice | 883824.33 | 4152 | 28000 | 813250 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 141
Belgrano & Clwyd Pump Station Review | 170000 | 0 | 0 | 10000 | 10000 | 150000 | 0 | 0 | 0 | 0 | 0 | 14
Rhyl & Gronannt Pump Station Review | 70000 | 0 | 0 | 20000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 3
Maes y Ffynnon Wall Refurbishment | 70000 | 0 | 0 | 10000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 9
Rhyl Cut & Prestatyn Gutter Fluvial Modelling | 68281 | 68281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
Warren Drive Trash screen | 35000 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Rhyl Sluice | 58605.74 | 1701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
Bodoryn & Gypsey Lane Pump Station Review | 20000 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 14
Ysgol Glan Morfa Embankment Refurbishment | 20000 | 0 | 0 | 5000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 21
Ffynnon y Ddol Culvert Works | 15000 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 14
Pont Robin Tidal Outfall Refurbishment | 332329.61 | 178945 | 11073.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141
St Asaph FCRM | 6695464.9 | 786354 | 93673 | 4000 | 3500 | 3500 | 3000 | 0 | 0 | 0 | 0 | 96
Flintshire - Sir y Fflint
Greenfield Embankment Improvements | 1636060 | 46060 | 140000 | 50000 | 100000 | 300000 | 1000000 | 0 | 0 | 0 | 0 | 187
Work arising from the Dee strategy | 88150000 | 0 | 0 | 0 | 150000 | 500000 | 500000 | 4000000 | 5000000 | 10000000 | 68000000 | 15
Point of Ayr | 516639.79 | 90691 | 408670 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92
Higherferry Queensferry & Rowleys Pump Station Review | 210000 | 0 | 0 | 40000 | 10000 | 10000 | 150000 | 0 | 0 | 0 | 0 | 15
Sealand - Northern Embankment Slump | 120000 | 0 | 0 | 20000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 38
Sealand & Thornleigh Pump Station Review | 120000 | 0 | 0 | 10000 | 10000 | 100000 | 0 | 0 | 0 | 0 | 0 | 38
Wepre Gutter Pilling Works | 111830 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
Beeches Drain Outfall | 60000 | 0 | 0 | 10000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 15
Rowleys Pumping Station Weedscreen | 25250 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
Broughton Brook & Queensferry Drain Modelling Study | 25000 | 0 | 0 | 5000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 15
Bretten Initial Assessment | 15000 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 15
Thornleigh PS Bank Stabalisation | 10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
Balderton Pump Station Review | 10000 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 15
Talacre Pumping Station Efficiency Improvements | 10000 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 92
Llong Floodgate | 6729 | 6729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 780
Gwynedd - Gwynedd
Mochras Flood Bank and Tidal Door | 3030000 | 0 | 0 | 0 | 0 | 0 | 30000 | 1000000 | 2000000 | 0 | 0 | 265
Dyfi Valley FWS Review | 2449079 | 43079 | 336000 | 20000 | 50000 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | n/a
Ty Gwyn Tidal Door Modelling | 2030000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 2000000 | 0 | 0 | 488
Porthmadog Tidal Structures | 1460001 | 35505 | 368000 | 50000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 20
Afon Rhyd Hir | 1100000 | 0 | 0 | 0 | 100000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 31
Llyn Tegid Reservoir Safety Works | 6711910.02 | 314776 | 1233130 | 4500281.78 | 411111.51 | 0 | 0 | 0 | 0 | 0 | 0 | 163
Dinas Dinlle Strategy | 370000 | 0 | 20000 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 119
Fairbourne & Barmouth - Tidal Flood Risk Modelling | 50000 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 51
Bontnewydd Wall Repair | 49950 | 49950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 426
Draenogau Tidal Doors | 80132 | 61554 | 6250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 488
Dysynni Low Level Outfall Tidal Doors Replacement | 184746.67 | 4619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145
CWRT Chamber & Weedscreen | 45000 | 0 | 0 | 15000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 1301
North West Culvert Inspection Programme | 40000 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Aberech Bank Reprofile | 39735 | 4235 | 35500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374
Llandanwg Breakwater | 35000 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 1779
Abererch Dune Repair Work 2018 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374
Afon Gwyrfai Flood Risk Study | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283
Afon Seiont Hydraulic Modeling | 19985 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244
Llyn Tegid Section 10 Repairs | 17722.23 | 3610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163
Dolgellau (Wnion and Arran) Flood Risk Management | 5560268.27 | 36691 | 43000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109
Penllyn Tywyn Outfall | 15000 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 145
Bwlch Coediog Blanket Bog | 14000 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Afon Bodfan Outfall Improvements | 5617 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220
Bala Sluice Auto Upgrade 2017 | 192376.44 | 146376.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163
Morfa Madryn Coastal Realignment | 49702.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Garndolbenmaen Gauging Station | 50294.439 | 48690.9 | 1603.359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1175
Fairbourne Flood Risk Management Scheme | 6326575.32 | 61919 | 127000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51
Ffriog Cliffs Sea Defence Repairs | 1549955.39 | 1367062 | 91093.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51
Isle of Anglesey - Sir Ynys Mon
Valley | 1540000 | 0 | 0 | 20000 | 20000 | 500000 | 1000000 | 0 | 0 | 0 | 0 | 121
Llangefni Flood Risk Study | 1446067 | 46067 | 100000 | 300000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 371
Amlwch | 575000 | 0 | 0 | 0 | 0 | 75000 | 500000 | 0 | 0 | 0 | 0 | 225
Dwyran Flood Risk Study | 37000 | 27000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244
Malltraeth Tidal Doors Replacement | 10602.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 278
Dwyran Flood Warning Monitoring Station | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244
Llangefni Flood Warning Monitoring Station | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 371
Merthyr Tydfil - Merthyr Tudful
Troedyrhiw - New FAS [RB] | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 69
Monmouthshire - Sir Fynwy
Sudbrook/Chepstow - Sea Defence Improvements | 1250000 | 0 | 100000 | 150000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 108
Monmouth Flood Gates - Improvements | 120000 | 0 | 0 | 20000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 25
Leys to Mathern Access | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292
Julians Reen Access Improvements and Wing Wall Repair | 58148 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101
Monmouth FAS – Embankment Repair | 90000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
Sea Doors - Asset Replacement Study | 27446 | 27446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
West Pill Outfall Improvments | 24049 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240
Caldicot and Wentlooge Sluice Improvement | 15978 | 15978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62
Caldicot and Wentlooge Model Update | 13619.7 | 6256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62
Selwyns Door - Culvert Replacement | 12610.75 | 3570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 338
Chepstow FAS - Gate Replacement | 53628.93 | 606 | 6449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108
Tafalog Gauging Station | 162805.44 | 12750 | 145017.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
Redbrook Gauging Station Refurbishment | 152892.8835 | 2397.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107
Portland Grounds Sea Defence Improvement | 2166372.52 | 29373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 182
Neath Port Talbot - Castell-nedd Port Talbot
Cadoxton Neath Initial Assessment | 430000 | 0 | 0 | 0 | 0 | 30000 | 200000 | 200000 | 0 | 0 | 0 | 28
Cwmafan Initial Assessment | 281436 | 10000 | 0 | 20000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 277
Pontardawe Industrial Area Defence | 175000 | 0 | 0 | 25000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 87
Resolven Weir Refurbishment | 118844.89 | 27643 | 8063.6425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77
Cilfrew Weir Refurbishment | 167808.57 | 10819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 266
Glynneath FAS Capital Maintenance | 150000 | 65000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154
Ffrwd Wyllt SMNR | 64755.05 | 22500 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
Trebanos Floodbank | 50000 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 85
Crynant Post Event Remedial Work | 92500.18 | 60000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311
Margam Initial Assessment | 30000 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 54
Neath Abbey IA | 25000 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 54
Ffrwd Wyllt Fluvial Initial Assessment | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
Aberdulais Evacuation Plan Reviews | 10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222
Port Talbot Gravel Removal | 5820 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
Resolven Aqueduct Improvements | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77
Cwm Clydach Dam Repairs | 143783.97 | 122825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
Newport - Casnewydd
Riverside Newport Flood Risk Management | 7756564.7 | 9271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
Stephenson Street, Liswerry | 9971290.77 | 281539 | 848000 | 6564000 | 1939000 | 176000 | 0 | 0 | 0 | 0 | 0 | 49
Tabbs Gout Sea Defence Improvements | 1675197.6 | 15050 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 356
Home Farm, Caerleon - New FAS | 70000 | 0 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 80
Riverside Newport - 90s Wall [Structural Assessment] | 40000 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 28
Tredegar Park Shoal Removal | 30000 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 69
Liswery Pill Model Update | 21234 | 21234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
Back Ditch | 20000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Crindau Pill Flood Risk Management Improvements | 14213808.44 | 2101478 | 1484655 | 1156281 | 13157 | 2527 | 0 | 0 | 0 | 0 | 0 | 26
Pembrokeshire - Sir Benfro
Haverfordwest Defences | 2230000 | 0 | 0 | 0 | 30000 | 200000 | 2000000 | 0 | 0 | 0 | 0 | 220
Pont y Cerbyd Reservoir Section 10 | 687114.92 | 558240 | 75550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 329
Ritec Culvert Improvements | 100000 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 341
Solva Catchment NFRM Project | 45446 | 21000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332
Tenby Buoy Assessment | 40000 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355
Pont y Cerbyd Access Improvements | 28698.21 | 2642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 329
Cartlett Brook Flood Wall | 15912 | 951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222
Little Haven | 15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 878
Stepaside Defences | 15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 929
Tenby Access | 10000 | 8000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355
Cilrhedyn Bridge | 12974.373 | 7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383
Powys - Powys
Disserth Gauging Station | 123953.32 | 19189.2 | 104000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216
Crickhowell IA | 110000 | 0 | 0 | 0 | 0 | 0 | 10000 | 100000 | 0 | 0 | 0 | 169
Brecon Embankment Repairs and Deshoal | 35000 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63
Glasbury - Structural Assessment | 30000 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 157
Llanwrytyd Wells | 20000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128
Llys Tawel Wall, Ystradgynlais | 15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158
Llanidloes Initial Assessment | 15000 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 140
Trehelig Door and Argae Refurbishment | 15000 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 284
Criggion Embankment | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 484
Prestigne Embankment | 10000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210
Ystradgynlais Flood Risk Management | 2488854.69 | 11357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158
Esgair Carnau - Bank Protection | 137140 | 101044 | 1989.784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
Cilmery Gauiging Station Refurbishment | 58619.8775 | 2331.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216
Rhondda Cynon Taf - Rhondda Cynon Taf
Robertstown IA | 3100000 | 0 | 0 | 0 | 0 | 100000 | 1000000 | 2000000 | 0 | 0 | 0 | 52
Treforest Industrial Estate | 1247080 | 47080 | 150000 | 50000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 62
Pontyclun Initial Assessment | 1115000 | 0 | 0 | 15000 | 100000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 79
Llwynypia Wall Repair | 1088043 | 136043 | 949000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77
Hirwaun - New FAS | 120000 | 0 | 0 | 20000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 129
River Rhondda Asset Management Plan | 110000 | 0 | 0 | 10000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 27
Hawthorn Shoal Removal | 72916 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122
Mountain Ash - Phase 2 | 70000 | 0 | 0 | 20000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 163
Nant Aman Culvert Screen | 50000 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 178
Treforest Deshoal | 40000 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68
Assessment of NFM Impacts in the Rhondda Valley | 40000 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Gelli Embankment & Deshoal | 40000 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21
Trehafod Blockstone Repairs | 35000 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 37
Mynydd Ton Peatbog Restoration | 31152.68 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Afon Cynon Integrated Catchment Model | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Ynysddu - Structural Assessment | 30000 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 65
Taffs Well Embankment | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267
Afon Clun Catchment NFM | 25000 | 3000 | 12000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Pontyclun Deshoal | 25000 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79
Rhondda Confluence | 25000 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 104
Glyntaff Initial Assessment | 15000 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 112
Aberdare Culvert Inspections | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44
Swansea - Abertawe
Cwm Ivy Marsh Managed Realignment | 552306.55 | 15000 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Pontarddulais Flood Risk Management | 6318681.34 | 347658 | 127000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65
Ynystawe Park Floodbank Repair | 113407.57 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 324
Nant y Fedrod Access | 30000 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80
Clydach & Glais & Ynystawe Mapping Study | 24000 | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Gorseinon FAS | 20000 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 294
Crofty River Channel Improvements | 20000 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 835
Ynystanglws Bank Wall Improvements | 16028.11 | 593.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1301
Llansamlet Initial Assessment | 15000 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 76
Gwynfe Road Floodbank Widening | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 351
The Vale of Glamorgan - Bro Morgannwg
Dinas Powys FAS | 5116655.94 | 213290 | 708125 | 3000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 29
Contribution to Coldbrook FAS | 1614229.55 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29
Cadoxton Sea Door Improvements | 871585.46 | 96213.75 | 647852.01 | 3814.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29
Torfaen - Torfaen
Llanyrafon, Cwmbran - Improve FAS | 1610000 | 0 | 0 | 10000 | 100000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 223
Ponthir Embankment | 55000 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134
Afon Llwyd Integrated Catchment Model | 25353 | 3227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Wrexham - Wrecsam
Bangor on Dee Embankment Slippage | 560000 | 0 | 0 | 10000 | 50000 | 500000 | 0 | 0 | 0 | 0 | 0 | 82
Bangor on Dee Embankment | 34259 | 10759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82
Trevalyn Pumping Station Review | 20000 | 0 | 0 | 10000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 345
Graig Lane Pumping Station Efficiency Improvements | 10000 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 75
Other
Wales FRM Capital Salaries | 13015829 | 1371811 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | n/a
Corporate FRM Capital Overhead Charges | 7000000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | n/a
FRM Transformation Programme | 6804073 | 344157 | 1200000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | n/a
NHCP Projects | 12400000 | 0 | 400000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | n/a
FRM Transformation - Replacement Flood Risk Asset Management System | 533459.73 | 177263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Flood Forecasting Hydrometric Improvements | 1279904.19 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | n/a
FRM Transformation - Telemetry Strategy | 1092129.5 | 264954.9 | 333200 | 283500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Wales FCRM Fleet Asset Replacement Programme 16/17 | 1309305.42 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Sea Outfall Maintenance Appraisal | 200000 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Transport and Plant Hydrometry (Contribution) | 368773.9 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | n/a
Landscape Maintenance | 246485.92 | 19290 | 5623 | 10918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Reservoir High Risk Designation | 103076 | 6186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Northern Area Pumping Station Review | 97807.5 | 255 | 81047.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
NRW PPMTs | 79809 | 4335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
FRM Transformation - River Levels Online | 215993 | 215993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
FRM Transformation - FEWS Phase 2 | 216986 | 216986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Reservoir Flood Designation Mapping 2017 | 655873.38 | 46271 | 449000 | 158250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Culverts Moving Forward Project | 60000 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | n/a
SW Access Areas | 55323.87 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Coastal Squeeze Monitoring Requirement Review | 45000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
NHCP Land Investigations and Feasibility | 338848.42 | 4876 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | n/a
FRM Transformation - NaFRA Replacement Product | 936692.69 | 628725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Upper Ely Integrated Catchment Model | 59204.74 | 29185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
NE Wales Tidal Defences Survey | 201488.17 | 1800 | 1800 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Northern Area Pumping Station Review - Phase 4A | 35545 | 725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
MEICA Asset Management Systems | 1018914.52 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | n/a
Lower Dee FWS Review | 25000 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Upper Dee FWS Review | 25000 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Culvert CCTV Survey Programme | 23325 | 23325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Llancarfan NFM | 23000 | 3000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Northen Area - Topographic Survey Requirements | 18750 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
North Wales Culvert Inspection and Maintenance | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
SE Topographic Data Collection 18/19 | 13175 | 13175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
CCTV Culvert Surveys SW | 11843 | 1160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Capital Maintenance Ops Delivery North | 2327499.83 | 0 | 0 | 0 | 0 | 260000 | 260000 | 260000 | 260000 | 260000 | 260000 | n/a
Capital Maintenance Ops Delivery South East | 1166511.75 | 0 | 0 | 0 | 0 | 130000 | 130000 | 130000 | 130000 | 130000 | 130000 | n/a
Capital Maintenance Ops Delivery South West | 1145565.34 | 0 | 0 | 0 | 0 | 130000 | 130000 | 130000 | 130000 | 130000 | 130000 | n/a
Northern Area Mapping | 983976.11 | 0 | 0 | 0 | 0 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | n/a
South East Area Mapping Projects | 1130691.46 | 0 | 0 | 0 | 0 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | n/a
South West Area Mapping projects | 812305.12 | 0 | 0 | 0 | 0 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | n/a
FRA Professional Advice | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
3rd Party Assets Strategy | 10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
FRA Scoping Assesment and Model Validation | 8375 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Public Safety Improvements 2018/19 | 5900 | 5900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a
Wales FCRM Fleet Asset Replacement Programme | 0 | 200000 | 800000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | n/a
Wales FCRM Fleet Asset Replacement Programme 17/18 | 576951 | 260405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a

## Appendix 2
Flood Risk Management Advisory Group 11th January 2019
Capital Programme Update Appendix 2 - Project Variances > +/- £50k
2018/19 Forecasts
Project | FRM AG (11/01/2019) (Works Done £k including risk allocation) | FRM AG (18/10/2018) (Works Done £k including risk allocation) | Variance: (Works Done £k) | Explanation
Cadoxton Sea Door Improvements (Barry) | 96214 | 840153 | -743939 | Contractors have demobilised from site and will be returning next financial year.
Stephenson Street, Liswerry (Newport) | 281539 | 758000 | -476461 | Previous forecast was based on costs within the Outline Business Case. Project has not progressed as quickly as originally planned, therefore a more realistic forecast has now been submitted.
Ffriog Cliffs Sea Defence Repairs (Fairbourne) | 1367062 | 1773421 | -406359 | Risk budget has been reviewed and the majority of these costs have been moved into next financial year. This includes costs for completing all construction accounts and any issues arising. Construction finish is due at the end of this financial year.
FRM Transformation Programme | 344157 | 690808 | -346651 | Cost expected to fluctuate as projects are removed from this forecast once approved and set up as stand alone projects. These project costs are reallocated to other specific costs codes.
Wales FCRM Fleet Asset Replacement Programme | 200000 | 400000 | -200000 | Decision made to concentrate on procuring high priority items this financial year. Items with long delivery times also removed.
Fairbourne Flood Risk Management Scheme | 61919 | 229500 | -167581 | Compensation costs and fees have all shifted into next financial year.
Reservoir Flood Designation Mapping 2017 | 46271 | 204551 | -158280 | Project start date was postponed due to funding confirmation delays and subsequent agreement of tender period with procurement. Project will now run into 19/20 and profile has been adjusted to reflect this.
Llyn Tegid Reservoir Safety Works (Bala) | 314776 | 469965 | -155189 | Drop in costs due to extended procurement timescales from previous estimate. Appointment of consultants has been delayed with consultancy fees, survey work and site investigation work being pushed into next financial year.
Pont y Cerbyd Reservoir Section 10 | 558240 | 638952 | -80712 | Risk forecast has been reducing as construction has been progressing well.
Ammanford FAS | 121045 | 181096 | -60051 | Ground Investigation costs removed as no longer required at this stage. Some risk cost has also been transferred into next year.
Gele Sluice (Afon Clwyd Estuary) | 2056 | 60212 | -58156 | Construction delayed until 20/21 due to delays with the Tidal Clwyd Strategy, change in costs to reflect this.
Roath and Rhymney Flood Risk Management (Cardiff) | 1950416 | 1867401 | 83015 | Increase due to update of construction costs following latest commercial meeting with contractors and compensation for businesses increased.
Llanfair Talhaiarn Phase 3 | 919292 | 816076 | 103216 | Slight increase in construction and supervision costs to reflect on-going site issues with regard to water main and transition structure levels.
St Asaph FCRM | 786354 | 632057 | 154297 | Construction cost increase as a result of final account agreement with contractors. Also, additional supervision costs due to extended programme (landscaping - watering requirements).
2019/20 Forecasts
Project | FRM AG (11/01/2019) (Works Done £k including risk allocation) | FRM AG (18/10/2018) (Works Done £k including risk allocation) | Variance: (Works Done £k) | Explanation
NHCP Projects | 400000 | 1500000 | -1100000 | Previous forecast was a generic estimate for future years requirements. Project mandates for specific project have since been submitted, giving a much more accurate forecast.
Llanfair Talhaiarn Phase 3 | 716803 | 829500 | -112697 | Reduction in costs after balancing construction costs following review.
Reservoir Flood Designation Mapping 2017 | 449000 | 556000 | -107000 | Tender prices have returned lower than forecasted but are yet to be assessed therefore forecast could change again following review.
White Barn North - Culvert Replacement (Conwy Valley) | 174050 | 279248 | -105198 | Project is now being managed by Projects Delivery, who have undertaken a full review of costs and submitted their own updated forecast.
Pencoed Initial Assessment | 0 | 100000 | -100000 | Prioritisation of projects have changed and the costs have been adjusted to reflect this. Project has moved into future years.
Resolven Aqueduct Improvements | 0 | 100000 | -100000 | Prioritisation of projects have changed and the costs have been adjusted to reflect this. Project has moved into future years.
Llangefni Flood Risk Study | 100000 | 50000 | 50000 | Project is still in development but project team feel that more funding will be required next year to progress the scheme than first estimated.
Gele Sluice (Afon Clwyd Estuary) | 52000 | 0 | 52000 | Construction delayed until 20/21, change in costs to reflect this.
Ammanford FAS | 150000 | 90000 | 60000 | Some risk transferred from this years profile. Ground Investigation moved from 18/19 to post preferred option stage.
Ffriog Cliffs Sea Defence Repairs (Fairbourne) | 91093.35 | 26000 | 65093.35 | Risk costs and fees relating to construction completion have been re-profiled into 19/20.
Llyn Tegid Reservoir Safety Works (Bala) | 1233130 | 1156797 | 76333 | Appointment of consultants has been delayed with consultancy fees, survey work and site investigation work being pushed into 19/20.
Northern Area Pumping Station Review | 81047.5 | 0 | 81047.5 | Project was originally on-hold and therefore no costs were forecasted. Following recent review, the project has been reprioritised and therefore will require funding next financial year.
Fairbourne Flood Risk Management Scheme | 127000 | 0 | 127000 | Compensation costs and fees have been profiled into this financial year.
Glynneath FAS Capital Maintenance | 150000 | 20000 | 130000 | Damage following Storm Callum has led to more maintenance work being identified. Due to the planning involved in engineering a solution and site restrictions costs have been placed in 19/20.
Cadoxton Sea Door Improvements (Barry) | 647852.01 | 4357 | 643495.01 | Contractors have demobilised from site and will be returning next financial year, therefore construction costs have been reprofiled.
FRM Transformation Programme | 1200000 | 206000 | 994000 | Initial forecast was purely to cover any carry over from 18/19 however new projects have now been added to next year's programme (which is still under review).